## Slide 1: Sprint Retrospective GROUP K

## Slide 2: Some numbers first
We have committed 4 stories out of 8 and managed to finish all the stories that we committed.
Total points of all stories were 26, and we committed and completed 13 of them.
On average we’ve spent around 3 hours per each task(some tasks took 2 hour and some 4 hours).

## Slide 3: Numbers, again
We have had 4 stories and 15 tasks so approximately 4 tasks per story.
Estimated hours per task were 2 and average was 2.6 hours, but as we mentioned before there were tasks that we under-estimated.
total task estimation error ratio ( = actual / estimated ) = 39/30=1. 3.

## Slide 4: Details
Story 1 5 Points 7 Tasks 18Hours
Story 2 3 Points 3 Tasks 9 Hours
Story 3. 3 Points 4 Tasks 10 Hours
Story 4 2 Points 2 Tasks 2 Hours
# of Tasks
Hours Spent
Story Points
TOTAL : 4 STORIES, 13 POINTS, 39 HOURS
ESTIMATED: 4 STORIES, 13 POINTS, 30 HOURS

## Slide 5: Cause of error
Lack of experience in estimation and project designing.
over estimations for our capability.
under estimations time needed for design and learning the needed technology.

## Slide 6: DEFINITION OF DONE
We sticked to the proposed DOD. We completed Unit Tests. We did a code review after we completed each story. We were using Github for version control and of course we did E2E Testing.

## Slide 7: What we have learned?
In this sprint we learned that the estimated time can differ in both positive and negative way, as soon as we didn’t know capacity of each member.
Also, we’ve learned the importance of daily scrum meetings, so we can know what problems each member has with his task.
How to divide tasks into a smaller ones so that we can work on daily basis.
We learned more about our capabilities so that we can estimate better next time.

## Slide 8: We are proud…
That we have delivered the product with all basic features working properly.
We managed to learn how to do GUI as no one of us knew how to use swing in java.

## Slide 9: Thank you all